## Objectives
1.0 Project Basics
1.1 Summarize the properties of a project.
• Temporary
• Start and finish
• Unique
• Reason/purpose
• Project as part of a program
• Project as part of a portfolio
1.2 Classify project roles and responsibilities.
• Sponsor/champion
- Approval authority
- Funding
- Project charter
- Baseline
- High-level requirements
- Control
- Marketing
- Roadblocks
- Business case/justification
• Project manager
- Manage team, communication, scope, risk, budget, and time
- Manage quality assurance
- Responsible for artifacts
• Project coordinator
- Support project manager
- Cross-functional coordination
- Documentation/ administrative support
- Time/resource scheduling
- Check for quality
• Stakeholder
- Vested interest
- Provide input and requirements
- Project steering
- Expertise
• Scheduler
- Develop and maintain project schedule
- Communicate timeline and changes
- Reporting schedule performance
- Solicit task status from resources
• Project team
- Contribute expertise to the project
- Contribute deliverables according to schedule
- Estimation of task duration
- Estimation of costs and dependencies
• Project Management Office (PMO)
- Sets standards and practices for organization
- Sets deliverables
- Provides governance
- Key performance indicators and parameters
- Provides tools
- Outlines consequences of non-performance
- Standard documentation/templates
- Coordinate resources between projects
1.3 Compare and contrast standard project phases.
• Initiation
- Project charter
- Business case
- High-level scope definition
- High-level risks
• Planning
- Schedule
- Work breakdown structure
- Resources
- Detailed risks
- Requirements
- Communication plan
- Procurement plan
- Change management plan
- Budget
• Execution
- Deliverables
• Monitor and control
- Risks/issues log
- Performance measuring and reporting
- Quality assurance/governance
- Change control
- Budget
• Closing
- Transition/integration plan
- Training
- Project sign off
- Archive project documents
- Lessons learned
- Release resources
- Close contracts
1.4 Identify the basics of project cost control.
• Total project cost
• Expenditure tracking
• Expenditure reporting
• Burn rate
• Cost baseline/budget
- Plan vs. actual
1.5 Identify common project team organizational structures.
• Functional
- Resources reporting to functional manager
- Project manager has limited or no authority
• Matrix
- Authority is shared between functional managers and project managers
- Resources assigned from functional area to project
- Project manager authority ranges from weak to strong
• Projectized
- Project manager has full authority
- Resources report to project manager
- Ad hoc resources
1.6 Given a scenario, execute and develop project schedules.
• Work breakdown structure
• Scheduling activities
- Determine tasks
- Determine task start/finish dates
- Determine activity/task durations
- Determine milestones
- Set predecessors
- Set dependencies
- Sequence tasks
- Prioritize tasks
- Determine critical path
- Allocate resources
- Set baseline
- Set quality gates
- Set governance gates
- Client sign off
- Management approval
- Legislative approval
1.7 Identify the basic aspects of the Agile methodology.
• Readily adapt to new/ changing requirements
• Iterative approach
• Continuous requirements gathering
• Establish a backlog
• Burndown charts
• Continuous feedback
• Sprint planning
• Daily standup meetings/ SCRUM meetings
• SCRUM retrospective
• Self-organized and self-directed teams
1.8 Explain the importance of human resource, physical resource, and personnel management.
• Resource management concepts
- Shared resources
- Dedicated resources
- Resource allocation
- Resource shortage
- Resource overallocation
- Low quality resources
- Benched resources
- Interproject dependencies
- Interproject resource contention
• Personnel management
- Team building
- Trust building
- Team selection
- Skill sets
- Remote vs. in-house
- Personnel removal/replacement
- Communication issues
- Conflict resolution
- Smoothing
- Forcing
- Compromising
- Confronting
- Avoiding
- Negotiating
2.0 Project Constraints
2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project.
• Common constraints
- Budget
- Scope
- Deliverables
- Quality
- Environment
- Resources
- Requirements
- Scheduling
• Influences
- Change request
- Scope creep
- Constraint reprioritization
- Interaction between constraints
- Stakeholders/sponsors/management
- Other projects
2.2 Explain the importance of risk strategies and activities.
• Strategies
- Accept
- Mitigate
- Transfer
- Avoid
- Exploit
• Risk activities
- Identification
- Quantification
- Planning
- Review
- Response
- Register
- Prioritization
- Communication
3.0 Communication & Change Management
3.1 Given a scenario, use the appropriate communication method.
• Meetings
- Kick-off meetings
- Virtual vs. in-person meetings
- Scheduled vs. impromptu meetings
- Closure meetings
• Email
• Fax
• Instant messaging
• Video conferencing
• Voice conferencing
• Face-to-face
• Text message
• Distribution of printed media
• Social media
3.2 Compare and contrast factors influencing communication methods.
• Language barriers
• Time zones/geographical factors
• Technological factors
• Cultural differences
• Interorganizational differences
• Intraorganizational differences
• Personal preferences
• Rapport building/relationship building
• Tailor method based on content of message
• Criticality factors
• Specific stakeholder communication requirements
- Frequency
- Level of report detail
- Types of communication
- Confidentiality constraints
- Tailor communication style
3.3 Explain common communication triggers and determine the target audience and rationale.
• Audits
• Project planning
• Project change
• Risk register updates
• Milestones
• Schedule changes
• Task initiation/completion
• Stakeholder changes
• Gate reviews
• Business continuity response
• Incident response
• Resource changes
3.4 Given a scenario, use the following change control process within the context of a project.
• Change control process
- Identify and document
- Evaluate impact and justification
- Regression plan (Reverse changes)
- Identify approval authority
- Obtain approval
- Implement change
- Validate change/quality check
- Update documents/audit documents/version control
- Communicate throughout as needed
• Types of common project changes
- Timeline change
- Funding change
- Risk event
- Requirements change
- Quality change
- Resource change
- Scope change
3.5 Recognize types of organizational change.
• Business merger/acquisition
• Business demerger/split
• Business process change
• Internal reorganization
• Relocation
• Outsourcing
4.0 Project Tools & Documentation
4.1 Compare and contrast various project management tools.
• Project scheduling software
• Charts
- Process diagram
- Histogram
- Fishbone
- Pareto chart
- Run chart
- Scatter chart
- Gantt chart
• Dashboard/status report
• Knowledge management tools
- Intranet sites
- Internet sites
- Wiki pages
- Vendor knowledge bases
- Collaboration tools
• Performance measurement tools
- Key performance indicators
- Key performance parameters
- Balanced score card
• SWOT analysis
• Responsible, Accountable, Consulted, Informed (RACI) Matrix
4.2 Given a scenario, analyze project centric documentation.
• Project charter
• Project management plan
• Issues log
• Organizational chart
• Scope statement
• Communication plan
• Project schedule
• Status report
• Dashboard information
• Action items
• Meeting agenda/meeting minutes
4.3 Identify common partner or vendor-centric documents and their purpose.
• Request for Information
• Request for Proposal
• Request for Quote
• Mutually binding documents
- Agreements/contract
- Non-disclosure agreement
- Cease and Desist letter
- Letter of Intent
- Statement of Work
- Memorandum of Understanding
- Service Level Agreement
- Purchase Order
- Warranty
Acronyms
AC
BAC
C&D
CCB
COQ
CPM
CV
EAC
ETC
EV
FF
FS
HR
IM
IMS
ISO
KPI
KPP
LOI
MOA
MOU
NDA
OBS
PM
PMO
PMP
PO
PV
RACI
RASCI
RFI
RFP
RFQ
RTM
SLA
SME
SOW
SS
SV
SWOT
WBS

## Objectives Table
Original Order | Indent | 0.0 Section | Section # | Section | 0.0 Subsection | Subsection $ | Subsection | Objective | Mastered
1 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.1 Summarize the properties of a project. | 1.1 | Summarize the properties of a project. | Temporary | 1
2 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.1 Summarize the properties of a project. | 1.1 | Summarize the properties of a project. | Start and finish
3 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.1 Summarize the properties of a project. | 1.1 | Summarize the properties of a project. | Unique
4 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.1 Summarize the properties of a project. | 1.1 | Summarize the properties of a project. | Reason/purpose | 1
5 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.1 Summarize the properties of a project. | 1.1 | Summarize the properties of a project. | Project as part of a program
6 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.1 Summarize the properties of a project. | 1.1 | Summarize the properties of a project. | Project as part of a portfolio
7 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Sponsor/champion | 1
8 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Approval authority
9 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Funding
10 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Project charter
11 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Baseline
12 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | High-level requirements
13 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Control
14 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Marketing
15 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Roadblocks
16 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Business case/justification
17 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Project manager
18 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Manage team, communication, scope, risk, budget, and time
19 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Manage quality assurance
20 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Responsible for artifacts
21 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Project coordinator
22 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Support project manager
23 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Cross-functional coordination
24 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Documentation/ administrative support
25 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Time/resource scheduling
26 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Check for quality
27 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Stakeholder
28 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Vested interest
29 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Provide input and requirements
30 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Project steering
31 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Expertise
32 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Scheduler
33 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Develop and maintain project schedule
34 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Communicate timeline and changes
35 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Reporting schedule performance
36 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Solicit task status from resources
37 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Project team
38 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Contribute expertise to the project
39 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Contribute deliverables according to schedule
40 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Estimation of task duration
41 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Estimation of costs and dependencies
42 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Project Management Office (PMO)
43 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Sets standards and practices for organization
44 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Sets deliverables
45 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Provides governance
46 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Key performance indicators and parameters
47 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Provides tools
48 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Outlines consequences of non-performance
49 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Standard documentation/templates
50 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.2 Classify project roles and responsibilities. | 1.2 | Classify project roles and responsibilities. | Coordinate resources between projects
51 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Initiation
52 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Project charter
53 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Business case
54 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | High-level scope definition
55 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | High-level risks
56 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Planning
57 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Schedule
58 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Work breakdown structure
59 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Resources
60 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Detailed risks
61 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Requirements
62 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Communication plan
63 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Procurement plan
64 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Change management plan
65 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Budget
66 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Execution
67 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Deliverables
68 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Monitor and control
69 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Risks/issues log
70 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Performance measuring and reporting
71 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Quality assurance/governance
72 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Change control
73 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Budget
74 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Closing
75 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Transition/integration plan
76 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Training
77 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Project sign off
78 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Archive project documents
79 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Lessons learned
80 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Release resources
81 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.3 Compare and contrast standard project phases. | 1.3 | Compare and contrast standard project phases. | Close contracts
82 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.4 Identify the basics of project cost control. | 1.4 | Identify the basics of project cost control. | Total project cost
83 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.4 Identify the basics of project cost control. | 1.4 | Identify the basics of project cost control. | Expenditure tracking
84 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.4 Identify the basics of project cost control. | 1.4 | Identify the basics of project cost control. | Expenditure reporting
85 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.4 Identify the basics of project cost control. | 1.4 | Identify the basics of project cost control. | Burn rate
86 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.4 Identify the basics of project cost control. | 1.4 | Identify the basics of project cost control. | Cost baseline/budget
87 | 2 | 1.0 Project Basics | 1.0 | Project Basics | 1.4 Identify the basics of project cost control. | 1.4 | Identify the basics of project cost control. | Plan vs. actual
88 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Functional
89 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Resources reporting to functional manager
90 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Project manager has limited or no authority
91 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Matrix
92 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Authority is shared between functional managers and project managers
93 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Resources assigned from functional area to project
94 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Project manager authority ranges from weak to strong
95 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Projectized
96 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Project manager has full authority
97 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Resources report to project manager
98 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.5 Identify common project team organizational structures. | 1.5 | Identify common project team organizational structures. | Ad hoc resources
99 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Work breakdown structure
100 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Scheduling activities
101 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Determine tasks
102 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Determine task start/finish dates
103 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Determine activity/task durations
104 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Determine milestones
105 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Set predecessors
106 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Set dependencies
107 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Sequence tasks
108 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Prioritize tasks
109 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Determine critical path
110 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Allocate resources
111 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Set baseline
112 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Set quality gates
113 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Set governance gates
114 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Client sign off
115 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Management approval
116 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.6 Given a scenario, execute and develop project schedules. | 1.6 | Given a scenario, execute and develop project schedules. | Legislative approval
117 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Readily adapt to new/ changing requirements
118 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Iterative approach
119 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Continuous requirements gathering
120 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Establish a backlog
121 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Burndown charts
122 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Continuous feedback
123 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Sprint planning
124 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Daily standup meetings/ SCRUM meetings
125 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | SCRUM retrospective
126 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.7 Identify the basic aspects of the Agile methodology. | 1.7 | Identify the basic aspects of the Agile methodology. | Self-organized and self-directed teams
127 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Resource management concepts
128 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Shared resources
129 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Dedicated resources
130 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Resource allocation
131 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Resource shortage
132 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Resource overallocation
133 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Low quality resources
134 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Benched resources
135 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Interproject dependencies
136 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Interproject resource contention
137 | 1 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Personnel management
138 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Team building
139 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Trust building
140 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Team selection
141 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Skill sets
142 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Remote vs. in-house
143 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Personnel removal/replacement
144 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Communication issues
145 | 3 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Conflict resolution
146 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Smoothing
147 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Forcing
148 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Compromising
149 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Confronting
150 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Avoiding
151 | 4 | 1.0 Project Basics | 1.0 | Project Basics | 1.8 Explain the importance of human resource, physical resource, and personnel management. | 1.8 | Explain the importance of human resource, physical resource, and personnel management. | Negotiating
152 | 1 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Common constraints
153 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Budget
154 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Scope
155 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Deliverables
156 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Quality
157 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Environment
158 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Resources
159 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Requirements
160 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Scheduling
161 | 1 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Influences
162 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Change request
163 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Scope creep
164 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Constraint reprioritization
165 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Interaction between constraints
166 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Stakeholders/sponsors/management
167 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.1 Given a scenario, predict the impact of various constraint variables and influences throughout the project. | 2.1 | Given a scenario, predict the impact of various constraint variables and influences throughout the project. | Other projects
168 | 1 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Strategies
169 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Accept
170 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Mitigate
171 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Transfer
172 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Avoid
173 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Exploit
174 | 1 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Risk activities
175 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Identification
176 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Quantification
177 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Planning
178 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Review
179 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Response
180 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Register
181 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Prioritization
182 | 3 | 2.0 Project Constraints | 2.0 | Project Constraints | 2.2 Explain the importance of risk strategies and activities. | 2.2 | Explain the importance of risk strategies and activities. | Communication
183 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Meetings
184 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Kick-off meetings
185 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Virtual vs. in-person meetings
186 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Scheduled vs. impromptu meetings
187 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Closure meetings
188 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Email
189 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Fax
190 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Instant messaging
191 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Video conferencing
192 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Voice conferencing
193 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Face-to-face
194 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Text message
195 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Distribution of printed media
196 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.1 Given a scenario, use the appropriate communication method. | 3.1 | Given a scenario, use the appropriate communication method. | Social media
197 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Language barriers
198 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Time zones/geographical factors
199 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Technological factors
200 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Cultural differences
201 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Interorganizational differences
202 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Intraorganizational differences
203 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Personal preferences
204 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Rapport building/relationship building
205 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Tailor method based on content of message
206 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Criticality factors
207 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Specific stakeholder communication requirements
208 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Frequency
209 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Level of report detail
210 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Types of communication
211 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Confidentiality constraints
212 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.2 Compare and contrast factors influencing communication methods. | 3.2 | Compare and contrast factors influencing communication methods. | Tailor communication style
213 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Audits
214 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Project planning
215 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Project change
216 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Risk register updates
217 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Milestones
218 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Schedule changes
219 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Task initiation/completion
220 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Stakeholder changes
221 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Gate reviews
222 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Business continuity response
223 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Incident response
224 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.3 Explain common communication triggers and determine the target audience and rationale. | 3.3 | Explain common communication triggers and determine the target audience and rationale. | Resource changes
225 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Change control process
226 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Identify and document
227 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Evaluate impact and justification
228 | 4 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Regression plan (Reverse changes)
229 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Identify approval authority
230 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Obtain approval
231 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Implement change
232 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Validate change/quality check
233 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Update documents/audit documents/version control
234 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Communicate throughout as needed
235 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Types of common project changes
236 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Timeline change
237 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Funding change
238 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Risk event
239 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Requirements change
240 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Quality change
241 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Resource change
242 | 3 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.4 Given a scenario, use the following change control process within the context of a project. | 3.4 | Given a scenario, use the following change control process within the context of a project. | Scope change
243 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.5 Recognize types of organizational change. | 3.5 | Recognize types of organizational change. | Business merger/acquisition
244 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.5 Recognize types of organizational change. | 3.5 | Recognize types of organizational change. | Business demerger/split
245 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.5 Recognize types of organizational change. | 3.5 | Recognize types of organizational change. | Business process change
246 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.5 Recognize types of organizational change. | 3.5 | Recognize types of organizational change. | Internal reorganization
247 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.5 Recognize types of organizational change. | 3.5 | Recognize types of organizational change. | Relocation
248 | 1 | 3.0 Communication & Change Management | 3.0 | Communication & Change Management | 3.5 Recognize types of organizational change. | 3.5 | Recognize types of organizational change. | Outsourcing
249 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Project scheduling software
250 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Charts
251 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Process diagram
252 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Histogram
253 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Fishbone
254 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Pareto chart
255 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Run chart
256 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Scatter chart
257 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Gantt chart
258 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Dashboard/status report
259 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Knowledge management tools
260 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Intranet sites
261 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Internet sites
262 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Wiki pages
263 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Vendor knowledge bases
264 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Collaboration tools
265 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Performance measurement tools
266 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Key performance indicators
267 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Key performance parameters
268 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Balanced score card
269 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | SWOT analysis
270 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.1 Compare and contrast various project management tools. | 4.1 | Compare and contrast various project management tools. | Responsible, Accountable, Consulted, Informed (RACI) Matrix
271 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Project charter
272 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Project management plan
273 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Issues log
274 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Organizational chart
275 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Scope statement
276 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Communication plan
277 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Project schedule
278 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Status report
279 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Dashboard information
280 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Action items
281 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.2 Given a scenario, analyze project centric documentation. | 4.2 | Given a scenario, analyze project centric documentation. | Meeting agenda/meeting minutes
282 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Request for Information
283 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Request for Proposal
284 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Request for Quote
285 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Mutually binding documents
286 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Agreements/contract
287 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Non-disclosure agreement
288 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Cease and Desist letter
289 | 3 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Letter of Intent
290 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Statement of Work
291 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Memorandum of Understanding
292 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Service Level Agreement
293 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Purchase Order
294 | 1 | 4.0 Project Tools & Documentation | 4.0 | Project Tools & Documentation | 4.3 Identify common partner or vendor-centric documents and their purpose. | 4.3 | Identify common partner or vendor-centric documents and their purpose. | Warranty